## Jira Backlogs
Issue Type | Summary | Description | Story Points | Assignee | Branch Name | Priority | Status
Task | create documentation | create SRS,jira task sheet, presentation,final report | 4 | Bhumi agarwal | document-setup | High | To Do
Task | English-Hindi Translator Web App | Complete development and deployment of translator web application using Flask and NLP model. | 20 | Project Lead | feature/epic-translator-app | High | To Do
Task | Setup Flask Project Structure | Initialize Flask app with folder structure, templates, static files. | 3 | Sushi Agarwal | feature/flask-setup | High | To Do
Task | Integrate Helsinki NLP Model | Load and configure Helsinki-NLP/opus-mt-en-hi model using transformers. | 5 | Rahul Sharma | feature/model-integration | High | To Do
Task | Create Translation API Route | Develop POST route to handle translation requests. | 3 | Priya Verma | feature/api-translation-route | Medium | To Do
Task | Design Frontend UI | Create responsive HTML/CSS interface for input and output display. | 5 | Ankit Singh | feature/frontend-ui | Medium | To Do
Task | Implement Error Handling | Handle empty input and server-side errors gracefully. | 2 | Sushi Agarwal | feature/error-handling | Medium | To Do
Task | Write Unit Tests | Create test cases for translation API and validation. | 3 | Rahul Sharma | feature/unit-tests | Low | To Do
Task | Create Requirements.txt & Procfile | Prepare dependencies file and configure gunicorn for deployment. | 2 | Priya Verma | feature/deployment-config | Medium | To Do
Task | Deploy on Render | Deploy application to Render and configure environment variables. | 5 | Project Lead | feature/render-deployment | High | To Do
Task | Documentation & README | Prepare project documentation and usage guide. | 2 | Ankit Singh | feature/documentation | Low | To Do